## Sheet1
SPRINT 1 BACKLOG
BACKLOG TASK | ASSIGNED TO | STATUS | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Backend Requirements Gathering
Frontend Requirements Gathering |  | Completed
Create sequence diagram for game |  | Completed
Create wireframe designs for the site
Create user stories |  | In progress
Create preliminary UI design |  | Completed
Finalise UI design |  | Completed
Finalise branding
Create branding pack
Analyse design justifications
Fully understand ethics proposal and its implications and share with the team | Joel
Setting up git repo | Fraser | Completed
Create folder and file structure for git management
Front-end interface implementation: Start page |  | Not Started
Front-end interface implementation: Single player main quiz page |  | Not Started
Front-end interface implementation: Quiz ended page |  | Not Started
Research implementation methods of continuous Integration and continuous delivery | Fraser
Reformat data into json format | Roman
Load data into mongoDB