## Sheet1
PRODUCT BACKLOG
USER STORY | AS A | I WANT TO BE ABLE TO... | SO THAT I CAN... | PRIORITY | ESTIMATE | SPRINT | STATUS
1 | Player | Set up and play a single player game | experience the game without the need for a team. | 10 | 25 | 2020-01-02 | In progress
2 | Player | Input a custom nickname | feel more engaged by the experience and uniquely identify myself from other players. | 9 | 8 | 2 | Not started
2020-03-04 | Player | Select a custom player icon and colour | to uniquely identify myself and allow other players to recognise me. | 9 | 8 | 2 | Not started
5 | Player | select 1 answer from the 4 given with each question | participate in the quiz in the way that was intended. | 10 | 10 | 2020-01-02 | In progress
6 | Player | receive random questions each round of the quiz | not be asked the same question multiple times in a quiz, or in quick succession of quizzes. | 9 | 3 | 1 | In progress
7 | Player | see my score update based on my answer. | be kept engaged with the game and each question. | 8 | 7 | 2 | Not started
8 | Player | recieve more points based on quickly I enter a correct answer | compete with other players to gain a score advantage and be rewarded for quickthinking. | 10 | 7 | 2 | Not started
9 | Player | exit a game anytime | leave a game at my convience. | 10 | 2 | 2 | Not started
10 | Player | play in a browser of my choosing | play the game regardless of what browser I use. | 10 | 7 | 2020-01-02 | In progress
11 | Player | join a multiplayer game | to play with my friends and have an engaging experience | 10 | 15 | 2020-01-02 | In progress
12 | Player | have a time limit to answer each question | create a competitive, fun atmosphere wth my friends | 10 | 12 | 2020-01-02 | In progress
13 | Player | Join a game only using a game code given to me by my friend | prevent myself from joining the wrong game | 9 | 7 | 2 | In progress
14 | Player | Be eliminated from a round if I am not doing well in game | Have a sense of competitiveness and excitement while playing | 5 | 7 | 2020-02-03 | Not Started
15 | Player | See real time leaderboard of my lobby | See how I am doing compared to everyone else | 7 | 8 | 2020-01-02 | In Progress
16 | Player | Receive trophy badges based on my actions in game | have more fun and be more competitivene | 4 | 6 | 3 | Not Started
17 | Player | Receive special items for getting random questions correct | get rewarded for continually getting answers correct | 2 | 7 | 3 | Not Started
18 | Player | Use items to affect my own or other player's scores | have more fun and more decision making elements | 2 | 8 | 3 | Not Started
19 | Player | Redeem myself and get back in the game if i am eliminated | keep playing and spice the game up | 4 | 6 | 3 | Not Started
20 | Host | Create a lobby | play with my friends online | 9 | 8 | 2020-01-02 | In Progress
21 | Host | Receive a unique game code to share with friends | only have my friends able to play in my lobby | 8 | 6 | 2020-01-02 | In Progress
22 | Developer | Implement voice over for questions | improve accesibility of app | 6 | 8 | 3 | Not Started
23 | Developer | Ensure colour contrasts meet WCAG guidelines | improve accessibility of app | 8 | 3 | 2020-01-02 | Not Started
24 | Developer | Ensure fonts meet WCAG guidelines | improve accessibility of app | 8 | 2 | 2 | Not Started
25 | Developer | Implement scoring system based on time taken to answer a question | keep the quiz competitive | 6 | 4 | 2 | Not Started
26 | Developer | Create & deploy a database | store all questions and answers | 10 | 5 | 1 | Complete
27 | Developer | Use multiple choice questions | easily interpret player's answers | 8 | 4 | 1 | Complete
28 | Developer | Connect lobby server to database | receive questions from database | 10 | 5 | 1 | In Progress
29 | Developer | Store lobby w/ unique game code | identify each game lobby | 9 | 8 | 2020-01-02 | In Progress
30 | Developer | Update scores after each round | keep players informed | 3 | 9 | 2 | Complete
31 | Developer | Send data in a JSON format | easily connect it to react frontend | 10 | 5 | 1 | In Progress