## Sheet1
SPRINT 1 BACKLOG
BACKLOG TASK | ASSIGNED TO | STATUS | PRIORITY | ORIGINAL ESTIMATE (hrs) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Backend Requirements Gathering | Backend Team | Completed | 8 | 3 | 3
Frontend Requirements Gathering | Frontend Team | Completed | 8 | 3 | 2 | 1
Create sequence diagram for game | Melvin | Completed | 6 | 1 | 1
Create user stories (Backend) | Backend Team | Completed | 8 | 3 | 2
Create user stories (Frontend) | Ruth, Kayla | Completed | 8 | 3 | 2 | 1 | 1
Create preliminary UI design | Ruth, Kayla | Completed | 8 | 5 | 4 | 2
Create logo graphics | Ruth | Completed | 5 | 1 | 1
Create graphics for player icons | Ruth | In progress | 6 | 2 | 1 |  | 1
Finalise UI design | Frontend Team | Completed | 8 | 2 |  | 2
Finalise branding | Alex | Completed | 5 | 1 |  | 1 | 1 | 1
Create branding pack | Alex | Completed | 5 | 4 |  |  | 2 | 3
Analyse design justifications | Ruth, Alex, Kayla | In progress | 7 | 3 |  |  | 3 | 3 | 2
Fully understand ethics proposal and its implications and share with the team | Joel | Completed | 5 | 2 |  | 1 | 1
Setting up git repo | Fraser | Completed | 9 | 0.5 |  |  | 0.5
Create folder and file structure for git management | Ruth | Completed | 4 | 0.5 |  |  | 0.5
Front-end interface implementation: Start page | Kayla | In progress | 7 | 4 |  |  | 3 | 3 | 2
Front-end interface implementation: Single player main quiz page | Frontend Team | In progress | 9 | 10
Front-end interface implementation: Quiz ended page | Frontend Team | In progress | 5 | 3
Research implementation methods of continuous Integration and continuous delivery | Fraser | Completed |  | 3 | 2 | 2 |  |  | 2
Testing implementation methods of continuous Integration and continuous delivery | Fraser | Completed | 8 | 4 |  | 3 | 4 |  | 2
Reformat data into json format | Roman | Completed | 7 | 2 |  | 3
Creation and hosting of Database | Patrick | Completed | 9 | 3 | 3
Load data into mongoDB | Patrick | Completed | 8 |  |  | 3
Create timer and countdown component | Danyal | Completed | 8 | 7
Create leaderboard component | Ruth | Completed | 8 | 7 |  |  | 4 | 4 | 4
Create answer buttons and question bar component | Joel | Completed | 8
Create header and main menu components | Kayla | Completed | 7
Create player identifier component | Melvin | Completed | 6 | 2
Refactor dataset import code to accomodate all data | Roman | Completed | 6 | 3 |  |  | 2 | 3
Create test web app to simulate how to integrate the application | Fraser | Completed | 5 | 5 |  |  | 1 | 5
Write python script to extract 10 random questions from the DB for a quiz round | Patrick | Completed | 6 | 2 |  |  | 2 | 2
Adapt previously developed server code to apply to our application | Ross | Completed | 8 | 6 |  | 3 | 2
Add functionality that allows client to join or host a new lobby with a randomly generated code | Ross | Completed | 8 | 5 |  |  | 1 | 4
Adapt previously developed client code to apply to our application | Melvin | Completed | 8 | 4 | 3 | 3
Allow backend server and DB to communicate | Patrick, Ross | In progress | 7 | 6 |  |  |  |  | 6
Allow client and server to communicate score information | Ross, Melvin | In progress | 7 | 4 |  |  |  |  | 3
Allow client and server to communicate chat information | Ross, Melvin | In progress | 6 | 4 |  |  |  |  | 3
Add functionality to timer component | Danyal | Not started | 8
Add functionality to answer buttons and question bar | Joel | Not started | 9
Add functionality to leaderboard | Ruth | Not started | 8
Add functionality to header and main menu | Kayla | Not started | 8
Add functionality to player identifier | Nazat | Not started | 6
Add components to main app page | Ruth | In progress | 9 | 4 |  |  |  |  | 3
122