## Sheet1
SPRINT 1 BACKLOG
BACKLOG TASK | ASSIGNED TO | STATUS | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Backend Requirements Gathering | Backend Team | In progress | 8
Frontend Requirements Gathering | Frontend Team | Completed | 8
Create sequence diagram for game | Melvin | Completed | 6
Create wireframe designs for the site |  | In progress | 7
Create user stories | Ruth, Kayla | In progress | 8
Create preliminary UI design | Ruth, Kayla | Completed | 8
Finalise UI design | Frontend Team | Completed | 8
Finalise branding | Alex | In progress | 5
Create branding pack | Alex | In progress | 5
Analyse design justifications | Ruth | Not started | 7
Fully understand ethics proposal and its implications and share with the team | Joel | Completed | 5
Setting up git repo | Fraser | Completed | 9
Create folder and file structure for git management | Ruth | Completed | 4
Front-end interface implementation: Start page | Kayla | In progess | 7
Front-end interface implementation: Single player main quiz page | Frontend Team | In progess | 9
Front-end interface implementation: Quiz ended page | Frontend Team | Not Started | 5
Research implementation methods of continuous Integration and continuous delivery | Fraser | In progress | 8
Reformat data into json format | Roman | Completed | 7
Load data into mongoDB | Patrick | Completed | 8
Create timer and countdown component | Danyal | In progess | 8
Create leaderboard component | Ruth | In progess | 8
Create answer buttons and question bar component | Joel | In progess | 8
Create header and main menu components | Kayla | In progess | 7
Create player identifier component | Nazat | In progess | 6