## Sheet1
BACKLOG TASK | ASSIGNED TO | STATUS | PRIORITY | ORIGINAL ESTIMATE (hrs) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
SPRINT 2 BACKLOG
Combine Frontend Components to one main application | Ruth, Danyal | Completed | 10 | 6 | 3
Style components in main app to fit design specifications | Danyal | In Progress | 9 | 3
Implement client to server handshake |  | In Progress | 10 | 6
Create Unit Tests for Database Queries |  | In Progress | 7 | 4
Begin writing up report |  | In Progress | 5 | 5
Implement Single Player gamemode |  | In Progress | 10 | 8
Implement joining lobby via code method |  | In Progress | 8 | 6
Implement Leaderboard for multiplayer games |  | In Progress | 6 | 5
Implement Devops method |  | In Progress | 7 | 6
Begin writing up ethical considerations |  | Not Started | 5 | 3
Implement nickname input and tracking |  | Not Started | 6 | 4
Implement Player icon and colour selection |  | Not Started | 6 | 4
Implement question answering function |  | Not Started | 8 | 4
Implement scoring system |  | Not Started | 8 | 5
Implement score tracking and updating |  | Not Started | 8 | 3
Implement elimination method |  | Not Started | 6 | 3
Asses WCAG guidelines for fonts |  | Not Started | 5 | 3
Asses WCAG guidelines for colour schemes |  | Not Started | 5 | 3
Begin working on presentation for end of project |  | Not Started | 4 | 6
Add functionality to timer component |  | Not Started | 8
•Reset timer on each round
•End round when the timer is up
•Add points to player score based off how fast they answer
Add functionality to answer buttons and question bar |  | Not Started | 9
•Check whether answer is correct/incorrect from DB
• Show visual change on screen when player inputs an answer
•Swap to new question when timer ends/everyone has answered
Add functionality to leaderboard |  | Not Started | 8
•Add points to every players score each round based on if the answer is correct and time answered
•Change player order on board based on score
Add functionality to player identifier |  | Not Started | 6
•Player identifier should change based on on the players inputted nickname
•Player identifier should change based on the players selected icon colour and image.
Add functionality to header and main menu |  | Not Started | 8
•Player should be able to select game mode from single player and multiplayer
•Players shoud be able to navigate back to the home page from any page usign the title
•Players should be able to exit out of a game at any time using an exit button
•Once a game mode is selected, allow player to enter nickname |  |  |  | Total:
•Once a game mode is selected, allow player to select an icon and colour |  |  |  | 87
•If multiplayer mode is selected, allow player to enter a lobby code and join a friends game